## Check list
Module | ID | Indicator | Test Description | Success Criteria | Run (Who/When) | Checked ✔️
ESP32 I2C Init | ESP-01 | AHT10 detected on I2C scan and read data | Detect and print raw values as depure logs on esp-idf terminal | Data obtain on terminal logs | Developer – Dev phase 1 |  | ok
ESP32 UART Out | ESP-02 | TX of sensor data from ESP32 at receive pattern | Use UART monitor on laptop to check data from ESP32 | Data in format XX.X,YY.Y | Developer – Dev phase 2 |  | ok
Lichee I2C Init | LIC-01 | SSD1306 responds on I2C scan | Use i2cdetect -y 0 to detect display | Address 0x3C visible in scan | Developer – Dev phase 1 |  | ok
Python OLED | LIC-02 | Display initialization script | Script displays welcome message | Message visible at startup | Developer – Dev phase 2
UART Receive | LIC-03 | Lichee receives and parses UART | Run UART listener script | Parsed values match what ESP32 sends | Developer – Dev phase 3
Display Update | LIC-04 | Data shown on SSD1306 | Data shown on display in real time | Display reflects latest UART reading | Developer – Dev phase 3
Lichee Wi-Fi AP Config | LIC-05 | Wi-Fi AP created and operational | Use hostapd/dnsmasq to configure Lichee as AP with static IP | Another device can connect to SSID and ping ip | Developer – Dev phase 4
HTTP Server Script Test | LIC-06 | HTTP server responds over network | Run Python Flask script, access via browser from another device | Web page displays sensor data correctly | Developer – Dev phase 4
HTTP Server Autostart | LIC-07 | HTTP server runs after boot | Create and enable systemd service for Flask web server | Web page accessible without manual server launch | Developer – Dev phase 4
Boot Autostart | LIC-08 | OLED script runs on boot | Use systemd to start script | Display updates without manual run | Developer – Final integration
Full Integration | INT-01 | End-to-end data flow | ESP32 → UART → Lichee → Display + Web | Sensor values displayed locally + on web | Dev + Test Team – Final milestone

## Requirements list
Hardware Setup | Connect AHT10 to ESP32 via I2C.
Connect SSD1306 to Lichee via I2C.
Connect ESP32 to Lichee via UART.
ESP32 Firmware Implementation | Initialize I2C bus and read AHT10.
Format sensor data for UART output.
Lichee Ubuntu Configuration | Enable I2C and UART interfaces.
Test SSD1306 using Adafruit CircuitPython library.
Create Python script for display logic.
Enable automatic script execution using systemd.
UART Communication | ESP32: configure UART TX.
Lichee: configure UART RX and parse data.
Display received data on OLED.
Network Configuration | Enable Lichee Wi-Fi AP mode.
Serve local web page with received sensor data.
Test connectivity and data access from other devices.
Testing & Validation | Unit testing of each module (sensor read, UART, display).
Integration tests with full flow.